## Sheet1
Few Hours | several hours | multiple days | Assessment
Sem 1 |  |  |  |  | Sem 2 | [6 empty] | Exam 8 - 22 jun
Week6-7 (27th Aug) | Week8-9 (10th Sep) | MidSem-Week10 (24th Sep) | Week11-12 (8th Oct) | Week13 (22nd Oct) | Week 1-2 (25th Feb) | Week3-4 (11th Mar) | Week5-6 (25th Mar) | Week7-8 (8th Apr) | Mid-Sem Week9 (22nd Apr) | Week10-11 (6th May) | Week12-13 (27th May) | Swotvac-Exam week 1 | Exam Week2-3
Start thesis draft. Create dedicated sections, perform more research on prosody, tibs, meaning, pauses | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Add ~5-7 pages of findings/notes to thesis progressively every week | Thesis = 10 June
Define a initial speech event class to model. This will either be pause or pitch related (most likely pause) as they are the only currnet implementations in Calpy. Build several pause and pitch profiles to understand what typical data looks like. Choose Conversations to draw speech event data (Try to choose typical conversation(s)) | Create synthetic conversations to test symbol sets on | Run tests measuring how effective Fast Entropy is at providing visual results | Continue Seminar Prep | Add, Refine, get feedback on further work for Seminar. End of semester should coincide with finishing implementation of a proof of concept for a pause based symbol set for classification | Use results of proto-alphabet to begin the process of creating a new symbol set for joint pause class | Evaluate Calpy for further improvements or refinements (do background research on how Calpy could be improved for conversational classification purposes) | Begin reimplemention steps from last semester to produce another symbol set for inner pause | Imolemet new symbolization technique | Produce symbol sets (have at least 5-10 symbol sets to work with | Start producing draft's for Poster | Poster = 24th May | Begin process of refining and drafting final thesis
Histogram of joint pause profiles (determine initial symbol set): Multiple varied conversations (to avoid single speaker bias), need to see broad range of data and how each range in computation time initially (what are ways I can average out grouped data sets). Goal is to find most accurate I can get without horrendous runtime. | Run the symbol sets on 5-10 normal conversations and 5 synthetic ones (to test accuracy). | Create synthetic conversations to run through the effectiveness of the initial alphabet (1 weeks), refine how it was produced and recreate alphabets continuously (1 weeks) implementaiton, synthetic and visualization is 6 weeks probs. Synthetic being controlled pause structure | Seminar (8th - 12th) | Use results to better understand effectiveness of symbol set and how to minimize (how to choose future base conversations, how to best use histograms, whether histograms are best choice, how many symbols proved to be redundant, how to best adjust entropy estimates) | Continue creaing a new joint pause class symbol set | Implement any ideas for improving Calpy | Choose Conversations to draw speech event data ( try to choose typical conversation(s)) | Discretization of inner pause profiles (determine initial symbol set): Multiple varied conversations (to avoid single speaker bias), need to see broad range of data and how each range in computation time initially. Goal is to find most accurate I can get without horrendous runtime | Run the symbol sets on 5-10 normal conversations and 5 synthetic ones (to test accuracy). | Analyze results to measure how well inner pause vs joint pause is | Repeat process of minimization for inner pause alphabet | Evaluate the system produced based on criteria from Goal C
Calpy tests: Find how well joint pause profiles match actual conversations | Change the way entropy is measured for each conversation and get various readings of accuracy | Prepare for seminar. Write outline, draft, time, refine, prepare slides | Analyze results to measure how well entropy works in this context (if possible match results to the conversations they came from to see if patterns or links can be drawn as to what kinds of conversations produce what kinds of results) |  | Evaluate inherent accuracy of a joint pause class (inner and uptake) as basis of entropy measurements and whether just inner pause classes are required | Implement a more effective pause profile for just inner pause in Calpy. This will combine pause and pitch profiles | Research for sophisticated techniques for discretizing the generated profiles than basic histograms | Calpy tests: Find how well inner pause profiles match actual conversations | Modify the way entropy is measured for each conversation and get various readings of accuracy | Use results to better understand effectiveness of symbol set and how to minimize (how to choose future base conversations, how to best use histograms, whether histograms are best choice, how many symbols proved to be redundant, how to best adjust entropy estimates) | Research what potential speech event classes will be most effective to add to Calpy, research how to implement into Calpy | Start producing diagrams/plots of symbolization, entropy estimations, classification ressults, etc…
Produce proto-alphabet sets (have at least 5-10 sets to work with (this may take a while to get to depending on how well I get calpy to work)) | Implement fast entropy methid into Calpy (2 weeks) implement (short), test, understand